QuickBite AI + Loyalty

System Architecture, Developer Tasks & Team Plan

DOCUMENT 6 OF 6  ·  VERSION 1.1

v1.1 — Security Developer role added across all sprint phases

Team: 7 members  ·  6 Weeks core build  ·  2 Weeks pen testing  ·  2 Weeks staging + launch

| Section 1 System Architecture Component map (19 components) Customer OTP data flow Security layer diagram Stitch.ai workflow + security gate | Section 2 Developer Task Timeline 12-week sprint plan 30 Security Dev tasks (SEC-01 to SEC-30) Pen test week (7–8) Pre-launch 17-point checklist | Section 3 ★ Team Role Assignments 7 roles including Security Developer Security Developer owns 30 tasks Updated RACI matrix (7 columns) Security phase-gate sign-off rules |
| --- | --- | --- |

Research-Backed  ·  Consensus.app peer-reviewed citations  ·  OTP + Stitch.ai + Security Developer

Research Findings — Consensus.app

Security design decisions are backed by peer-reviewed research. The Security Developer ensures all mitigations are correctly implemented.

| Research Finding | Application + Security Dev Verification |
| --- | --- |
| OTP with TOTP + HOTP significantly strengthens 2FA (Acosta Mayorga et al., 2025) | Customer loyalty OTP login. Security Dev verifies crypto randomness via `secrets.token_digits(6)` in SEC-05. |
| SMS OTP vulnerable without rate limiting + expiry enforcement (Zhao et al., 2025) | Rate limits enforced. Security Dev verifies 3-attempt limit, 2-min cooldown, 5/day cap in SEC-07. |
| MFA combining OTP + biometrics improves mobile app security (Ali et al., 2021) | TOTP for Owner/Manager. Security Dev audits TOTP RFC 6238 compliance in SEC-03. |
| Customer PII in loyalty programs requires AES encryption under GDPR/CCPA (Amama et al., 2024) | AES-256-GCM for all PII. Security Dev audits key entropy, IV randomness, no plaintext in DB in SEC-09. |
| Usability issues are primary barrier to MFA adoption (Baseer, 2024) | Customer OTP is single-screen, 30-second, auto-fill. Security Dev ensures friction only where warranted. |
| Digital membership systems increase visit frequency (Ariyanti et al., 2025) | OTP loyalty login built on Security Dev-approved architecture. |

Section 1.  System Architecture

Complete picture of every component in QuickBite AI + Loyalty. Security boundaries marked 🔐.

→  1.1  Architecture Overview

| Surface | Technology | Users |
| --- | --- | --- |
| Customer PWA | Stitch.ai + Jinja2 + Tailwind CSS | Diners scanning QR codes — review + loyalty + OTP login |
| Restaurant Dashboard | Stitch.ai + Jinja2 + Chart.js + GSAP | Owner / Manager / Staff |
| Super Admin Panel | Stitch.ai + Jinja2 | QuickBite internal team |

→  1.2  Security Architecture Layers  🔐

Security Developer owns all layers marked 🔐 below:

🔐 PERIMETER LAYER ▸ Cloudflare WAF + Bot Detection + DDoS protection ▸ TLS 1.3 only — enforced at edge before request reaches FastAPI

🔐 APPLICATION LAYER ▸ SlowAPI rate limits: IP-based + tenant-based + OTP-specific (SEC-07) ▸ Pydantic v2 input validation on ALL endpoints — no raw input reaches DB ▸ prompt_guard.py — LLM injection prevention (SEC-12) ▸ Authlib PKCE OAuth flow — code interception prevention (SEC-11)

🔐 AUTHENTICATION LAYER ▸ PyJWT + bcrypt w12 + PyOTP TOTP for Owner/Manager (SEC-03) ▸ Python secrets.token_digits(6) + SHA-256 hash for Customer OTP (SEC-05) ▸ AES-256-GCM encryption for all PII at rest (SEC-09) ▸ Separate SECRET_KEY and CUSTOMER_SECRET_KEY — never the same (SEC-08)

🔐 DATA LAYER ▸ PostgreSQL RLS on all 15 tenant-scoped tables (SEC-04, SEC-23) ▸ SHA-256 hashed indexes — no raw phone/email in query indexes (SEC-09) ▸ AES-256-GCM encrypted columns: phone, email, name ▸ Append-only audit_logs table — immutable security event record

🔐 CI/CD SECURITY LAYER ▸ bandit — Python static analysis on every PR (SEC-02) ▸ trivy — Docker image CVE scan in CI pipeline (SEC-02) ▸ safety — Python dependency CVE scan (SEC-02) ▸ git-secrets hook — prevents secret commits to repo (SEC-02) ▸ OWASP ZAP — automated DAST scan on staging (SEC-21)

→  1.3  Customer OTP Data Flow

The complete journey from QR scan to stamp logged. Security Dev verification points marked.

| # | Technology | Action | Security Dev Check |
| --- | --- | --- | --- |
| 1 | FastAPI middleware | Branch QR token → tenant_id resolved via Redis | — |
| 2 | Stitch.ai + Jinja2 + Tailwind | Loyalty card page renders in browser | SEC-02: CSP-compatible HTML verified |
| 3 | SlowAPI + Redis | OTP request rate-checked (1/2min per phone) | SEC-07: Rate limit enforced at middleware level |
| 4 | Python secrets | secrets.token_digits(6) generates OTP | SEC-05: Verify NOT random.randint() in code review |
| 5 | Redis | SHA-256(otp) stored with EX 300 (5-min TTL) | SEC-05: Verify hash stored, not plaintext OTP |
| 6 | Twilio SMS | OTP delivered to customer's phone | SEC-06: Unknown phone → 200 not 404 (enumeration prevention) |
| 7 | PyJWT | Customer JWT issued (7-day, HttpOnly cookie) | SEC-08: Verify CUSTOMER_SECRET_KEY ≠ SECRET_KEY |
| 8 | PostGIS ST_DWithin | GPS distance from branch calculated (<10ms) | SEC-13: Verify is_fraudulent=true cannot be bypassed |
| 9 | PostgreSQL + RLS | Stamp logged in stamp_logs table | SEC-23: Verify RLS isolates per tenant_id |
| 10 | Celery + Redis | Reward dispatch task if threshold reached | SEC-15: Verify idempotency key prevents duplicate rewards |
| 11 | Twilio WhatsApp | Reward notification sent (Pro+ only) | SEC-30: WhatsApp webhook verified signed |
| 12 | OpenTelemetry + Sentry | Trace + errors captured | SEC-29: Sentry PII scrubbing verified |

Section 2.  Developer Task Timeline

12-week sprint plan. Security Developer tasks (SEC-01 to SEC-30) integrated at every phase.

ℹ   Team size: 7 — Backend Dev 1, Backend Dev 2, Frontend Dev, DevOps, QA, Security Developer, Product Manager.

12-Week Sprint Overview

| Weeks | Phase | Key Deliverables | Status Gate | Security Gate |
| --- | --- | --- | --- | --- |
| 1–2 | Foundation | Skeleton, auth, RBAC, multi-tenancy | Auth flows fully tested | 🔐 SEC-01 to SEC-04 passed |
| 3 | OTP + Billing | Customer OTP, registration, Stripe | OTP < 10s delivery | 🔐 SEC-05 to SEC-10 passed |
| 4–6 | Core Features | Review engine, loyalty, dashboard | E2E flow tested | 🔐 SEC-11 to SEC-16 passed |
| 7–8 | Pen Test + QA | Admin, full pen test, load test | P95 < 500ms | 🔐 SEC-17 to SEC-24: 0 criticals |
| 9–10 | Staging + Pilot | Deploy, pilot restaurants | 2 pilots live | 🔐 SEC-25 to SEC-28 signed off |
| 11–12 | Launch | Production, security monitoring | First paying customer | 🔐 SEC-29 + SEC-30 done |

→  Weeks 1–2:  Foundation  (ALL TEAM)

| Ticket | Task | Description | Assigned To |
| --- | --- | --- | --- |
| INFRA-01 | Project Skeleton | FastAPI skeleton, folder structure, requirements, config, ruff setup | All devs |
| INFRA-02 | PostgreSQL + PostGIS | Async engine, base models, Alembic, PostGIS enabled | Backend Dev 1 |
| INFRA-03 | Redis + Celery | Cache service, broker, connection pool | Backend Dev 2 |
| Stitch.ai | Design System Setup | Workspace setup, QuickBite design tokens, first component export | Frontend Dev |
| DevOps | Docker + Compose | Full local stack: FastAPI + PG + Redis + Celery | DevOps Eng |
| 🔐 SEC-01 | Threat Model | Map all attack surfaces. OTP, JWT, RLS, PII, OAuth, Stripe webhooks. Document threats and mitigations. | Security Dev |
| 🔐 SEC-02 | CI Security Toolchain | Integrate bandit, trivy, safety, git-secrets into GitHub Actions. Block PRs on High+ findings. | Security Dev |
| AUTH-01 | User Registration | Email + password + verification email. bcrypt w12. Tenant provision on verify. | Backend Dev 1 |
| AUTH-02 | Login + TOTP MFA | 2-step login: password → MFA session token → TOTP → JWT. Rate-limited. | Backend Dev 1 |
| AUTH-03 | JWT Refresh Rotation | Single-use refresh rotation. jti revocation in Redis on logout. | Backend Dev 1 |
| AUTH-04 | RBAC Guards | require_role(), check_subscription_tier() FastAPI dependencies. | Backend Dev 2 |
| TENANT-01 | Subdomain Middleware | Host header → tenant_id → Redis lookup → request.state injection. | Backend Dev 2 |
| TENANT-02 | RLS Policies | PostgreSQL RLS on all 15 tenant-scoped tables. Alembic migration. | Backend Dev 2 |
| 🔐 SEC-03 | Auth Security Audit | Verify: bcrypt w12, JWT HS256 (not 'none'), 256-bit SECRET_KEY, TOTP RFC 6238 compliance, refresh single-use, jti revocation works. | Security Dev |
| 🔐 SEC-04 | RLS Policy Audit | Write cross-tenant SQL test queries. Verify 0 rows returned for Tenant B when logged in as Tenant A. Test with psql directly. | Security Dev |

→  Week 3:  OTP + Billing  ★ Security Dev Critical Week

| Ticket | Task | Description | Assigned To |
| --- | --- | --- | --- |
| SUB-01 | Subscription Plans + Stripe | Seed 3 plans. Stripe Checkout sessions. Webhook handler with signature verification. | Backend Dev 1 |
| SUB-02 | Usage Tracking + Gating | Monthly counters per tenant. check_plan_limit() dependency. 80% / 100% thresholds. | Backend Dev 2 |
| NEW-OTP-01 | Customer OTP Request | POST /auth/customer/otp-request. Phone + email variants. Rate-limited. Redis store. | Backend Dev 1 |
| NEW-OTP-02 | Customer OTP Verify | POST /auth/customer/otp-verify. Hash compare. 3-attempt limit. Customer JWT issue. | Backend Dev 1 |
| NEW-OTP-03 | Customer Registration | POST /customers/register. Encrypted PII. Seamless flow when user not found. | Backend Dev 2 |
| Stitch.ai | OTP + Register Screens | OTP login screen (6-box) + customer registration screen (pre-filled phone). | Frontend Dev |
| 🔐 SEC-05 | OTP Crypto Audit | Verify secrets.token_digits(6) not random.randint(). Verify SHA-256(otp) stored (not plaintext). Verify Redis TTL = exactly 300s. | Security Dev |
| 🔐 SEC-06 | Enumeration Prevention | Verify unknown phone → HTTP 200 + {status:'new_user'} NOT 404. Prevents attacker from discovering registered phones via timing or status code. | Security Dev |
| 🔐 SEC-07 | OTP Rate Limit Tests | Automate: confirm 3rd wrong attempt deletes Redis key. Confirm 2-min cooldown blocks. Confirm 6th daily request returns 429. | Security Dev |
| 🔐 SEC-08 | Customer JWT Isolation | Verify CUSTOMER_SECRET_KEY ≠ SECRET_KEY. Verify customer JWT rejected on owner routes (403). Verify owner JWT rejected on customer routes (401). | Security Dev |
| 🔐 SEC-09 | PII Encryption Audit | Verify AES-256-GCM key is 256-bit. Verify IV is random per call. Run SQL: confirm no phone/email in plaintext anywhere in DB columns or indexes. | Security Dev |
| 🔐 SEC-10 | Stripe Webhook Security | Verify stripe.Webhook.construct_event() called before any processing. Test with invalid signature: must return 401, no side effects. | Security Dev |

→  Weeks 4–6:  Core Features  (PARALLEL + SECURITY TRACKS)

| Wk | Backend Track | Frontend Track | 🔐 Security Dev Track |
| --- | --- | --- | --- |
| 4 | REVIEW-01 (composer), REVIEW-03 (GMB OAuth), LOYALTY-01 (branch + GPS) | Review composer page, Loyalty card UI, OTP flow wired to API | SEC-11: Audit PKCE implementation in GMB OAuth. Verify code_verifier is random, code_challenge is SHA-256. SEC-12: Test prompt injection via review tags field — verify prompt_guard.py blocks. |
| 5 | LOYALTY-02 (QR), LOYALTY-03 (geofence + stamp), REVIEW-02 (AI drafts) | Stamp Collected animation, OTP login + registration wired, Dashboard skeleton | SEC-13: Geofence fraud audit — test with spoofed GPS. Verify is_fraudulent=true set correctly. SEC-14: QR token entropy — verify secrets.token_urlsafe(32). Test brute-force resistance. |
| 6 | LOYALTY-04 (rewards + redemption), DASH-01 (dashboard + WS), DASH-02 (analytics) | Dashboard stats row + review list + approval buttons, Branch management + QR download | SEC-15: Celery idempotency — verify duplicate reward cannot dispatch on retry. Test by triggering task twice with same idempotency key. SEC-16: WebSocket — verify JWT required to subscribe, tenant_id enforced on all WS pushed events. |

→  Weeks 7–8:  Penetration Testing + Polish  ★ Security Dev Peak Sprint

| Ticket | Task | Description | Assigned To |
| --- | --- | --- | --- |
| ADMIN-01 | Super Admin Panel | Platform-wide view, force-logout, audit log, manual GMB sync trigger. | Backend Dev 1 |
| SUB-03 | Upgrade Flow | Stripe Checkout + billing portal + plan refresh on webhook. | Backend Dev 2 |
| Stitch.ai | Admin + Billing Screens | Admin panel, upgrade modal, subscription billing page. | Frontend Dev |
| QA Suite | Integration Tests | Auth flows, OTP flows, loyalty flows, RLS isolation tests. | QA Engineer |
| Load Test | Locust 100 concurrent | All key endpoints under load. P95 < 500ms gate. | DevOps |
| 🔐 SEC-17 | Pen Test Plan | Write full penetration test plan. 8 attack categories: auth bypass, OTP attacks, injection, SSRF, replay, privilege escalation, JWT attacks, loyalty fraud. | Security Dev |
| 🔐 SEC-18 | Auth Bypass Tests | JWT 'none' algorithm attack. Algorithm confusion. Expired token reuse. Cross-role token. TOTP replay within window. Force-logout bypass attempt. | Security Dev |
| 🔐 SEC-19 | OTP Attack Tests | Brute-force 3-attempt lockout. OTP replay after expiry. Phone enumeration via timing analysis. Redis key collision attempt. Daily limit bypass. | Security Dev |
| 🔐 SEC-20 | Injection Tests | SQL injection via all Pydantic inputs. LLM prompt injection via review tags. XSS via restaurant name in HTML template. SSRF via GMB callback URL. | Security Dev |
| 🔐 SEC-21 | OWASP ZAP Scan | Automated dynamic scan on staging. All High + Critical findings must be remediated before staging sign-off. | Security Dev |
| 🔐 SEC-22 | Burp Suite Manual Test | Intercept OTP flow. Replay attacks on loyalty scan. Tamper with JWT tenant_id claim. Modify Stripe webhook payload. SSRF via httpx paths. | Security Dev |
| 🔐 SEC-23 | RLS Final Verification | Log in as Tenant A. Execute 10 different SELECT * queries. Confirm 0 rows from Tenant B across all 15 RLS-protected tables. Document each test result. | Security Dev |
| 🔐 SEC-24 | Security Findings Report | Document all findings: severity (Critical/High/Medium/Low), evidence, affected endpoint, remediation step. Share with all devs. Track in security backlog. | Security Dev |
| Bug Fixes | All Fixes | Triage and fix issues from QA + load test + security pen test. | All devs |

→  Weeks 9–10:  Staging + Pilot + Security Sign-Off

| Ticket | Task | Description | Assigned To |
| --- | --- | --- | --- |
| Deploy | Staging Deploy | Full environment parity with production. | DevOps |
| E2E Test | Pilot Restaurants | End-to-end with real QR codes, real SMS OTPs, real GMB. 2–3 pilot restaurants. | PM + All devs |
| 🔐 SEC-25 | Remediation Verify | Re-test all findings from SEC-24 report. All Critical and High findings must be resolved before launch sign-off. Security Dev confirms. | Security Dev |
| 🔐 SEC-26 | SECURITY.md | Write: responsible disclosure policy, security contact email, scope of security programme, out-of-scope items. | Security Dev |
| 🔐 SEC-27 | RUNBOOK.md | Write: incident response steps, SECRET_KEY rotation procedure, DB restore procedure, how to force-logout all users, OTP abuse escalation guide. | Security Dev |
| 🔐 SEC-28 | Pre-Launch Checklist | 17-point security checklist signed off by Security Dev before any production deploy is authorised. | Security Dev |

→  Weeks 11–12:  Production Launch + Security Monitoring

| Ticket | Task | Description | Assigned To |
| --- | --- | --- | --- |
| Launch | Production Deploy | Deploy to production. Monitor error rate, P95, queue depth. | DevOps |
| Sales | First Customer | Sales outreach. First paying customer target. | PM |
| 🔐 SEC-29 | Security Monitoring Setup | Sentry alert rules for auth anomalies. Prometheus alert for OTP spike > 100/min. Grafana dashboard: failed login rate, geofence rejection rate, JWT revocation rate. | Security Dev |
| 🔐 SEC-30 | Incident Response Drills | Simulate: compromised JWT (force-logout all), leaked SECRET_KEY (rotation drill), PostgreSQL RLS bypass attempt, Stripe webhook replay attack. | Security Dev |
| Retro | Sprint Retrospective | Measure PRD success metrics. Identify v1.1 priorities. | PM |
| v1.1 Plan | v1.1 Roadmap | Scratch cards, WhatsApp, CRM campaigns, Yelp integration. | PM + All devs |
| Ongoing | Weekly Security Scans | bandit + trivy + safety results reviewed weekly. 90-day SECRET_KEY rotation reminder tracked. | Security Dev |

🔒   Pre-Launch Security Checklist (17 points) — Security Dev must sign off EACH item before production deploy is authorised.

| # | Security Check | Verified By |
| --- | --- | --- |
| 1 | ☐ OWASP Top-10 self-audit completed and documented | Security Dev |
| 2 | ☐ All auth endpoints tested for brute-force, token reuse, and session fixation | Security Dev |
| 3 | ☐ RLS verified: Tenant A cannot access Tenant B's data via any SQL path | Security Dev |
| 4 | ☐ OTP enumeration prevention: unknown phone → 200 (not 404) | Security Dev |
| 5 | ☐ OTP crypto: secrets.token_digits(6) confirmed in code review — NOT random.randint() | Security Dev |
| 6 | ☐ CUSTOMER_SECRET_KEY ≠ SECRET_KEY in production environment | Security Dev |
| 7 | ☐ AES-256-GCM: key is 256-bit, IV random per call, no plaintext PII in DB | Security Dev |
| 8 | ☐ JWT revocation: revoked jti rejected within 15 seconds | Security Dev |
| 9 | ☐ Refresh token reuse: replaying old token revokes all sessions | Security Dev |
| 10 | ☐ All bandit CI scans green (no High/Critical Python security findings) | Security Dev + DevOps |
| 11 | ☐ trivy Docker scan: no Critical CVEs in final production image | Security Dev + DevOps |
| 12 | ☐ OWASP ZAP automated scan: no High/Critical findings on staging | Security Dev |
| 13 | ☐ Burp Suite manual testing: no critical auth bypass found | Security Dev |
| 14 | ☐ SECURITY.md committed to repo with disclosure policy | Security Dev |
| 15 | ☐ RUNBOOK.md committed with incident response steps | Security Dev |
| 16 | ☐ Sentry PII scrubbing: no phone/email in error events (verified in staging) | Security Dev |
| 17 | ☐ Stripe webhook signature verification confirmed in production environment | Security Dev + Backend Dev 1 |

Section 3.  Team Role Assignments

7 roles. Security Developer added in v1.1 — owns 30 security tasks (SEC-01 to SEC-30) and phase-gate sign-off authority.

→  3.1  Role Definitions  (7 Roles)

⚙️ Backend Dev 1 Owns: ✓ Auth system: password, TOTP MFA, customer OTP (NEW-OTP-01/02/03), OAuth ✓ AI engine: GPT-4o + Gemini + feature-flag failover ✓ GMB service: OAuth + incremental review sync + response posting ✓ Billing service: Stripe checkout, subscription webhooks Collaborates with: Backend Dev 2 for schema design. Frontend Dev for API contracts. Security Dev for auth PR reviews (mandatory). Key skills: Python, FastAPI, SQLAlchemy, PyJWT, Twilio, OpenAI

🗄️ Backend Dev 2 Owns: ✓ PostgreSQL schema + PostGIS geometry + Alembic migrations ✓ Row-Level Security policies on all 15 tables ✓ Geofence service: PostGIS ST_DWithin calculations ✓ Loyalty service: stamp logging, reward unlocking, scratch cards ✓ Usage tracking + plan gating + monthly counter resets Collaborates with: Backend Dev 1 for auth + AI. DevOps for DB provisioning. Security Dev for RLS policy review (mandatory). Key skills: Python, PostgreSQL, PostGIS, GeoAlchemy2, Redis, Celery

🎨 Frontend Dev Owns: ✓ All screens via Stitch.ai — generate, refine, review, export ✓ Customer OTP login (6-box), registration (pre-filled), loyalty card, stamp celebration ✓ Review composer: star rating, tags, AI draft, copy buttons ✓ Dashboard: stats row, review list, loyalty analytics, Chart.js ✓ Landing page: Three.js 3D hero, GSAP scroll animations Collaborates with: Backend devs for API endpoints. PM for UX review. Security Dev for CSP-compatible HTML review. Key skills: Stitch.ai, Jinja2, Tailwind CSS, JavaScript, GSAP, Three.js, Chart.js

🐳 DevOps Engineer Owns: ✓ Docker + docker-compose: full local dev stack ✓ GitHub Actions CI/CD: lint, test, security scan, build, staging, manual prod gate ✓ Staging + production deployment (Railway or AWS ECS) ✓ Monitoring: Prometheus + Grafana + Sentry alerts ✓ Secret management: AWS Secrets Manager + 90-day rotation tracking ✓ Database backups: Supabase PITR + quarterly restore drill Collaborates with: All devs. Security Dev for CI security tool integration and secrets management strategy. Key skills: Docker, GitHub Actions, Nginx, AWS, Terraform, Grafana

🔍 QA Engineer Owns: ✓ Integration test suite: pytest + httpx. All endpoint flows. ✓ OTP flow tests: phone, email, new user redirect, rate limits ✓ RLS cross-tenant isolation: functional correctness tests ✓ Load testing: Locust — 100 concurrent users on all key endpoints ✓ Pre-launch functional checklist (separate from Security Dev's security checklist) Collaborates with: Security Dev: QA tests functional correctness, Security Dev tests attack vectors — complementary, not overlapping. Key skills: pytest, Locust, Postman, httpx, GitHub Actions

🔐 Security Developer Owns: ✓ SEC-01: Threat model — all attack surfaces documented ✓ SEC-02: CI security toolchain: bandit, trivy, safety, git-secrets ✓ SEC-03: Auth security audit: bcrypt w12, JWT HS256, 256-bit keys, TOTP RFC 6238 ✓ SEC-04 + SEC-23: RLS policy correctness — cross-tenant SQL tests ✓ SEC-05: OTP crypto audit: secrets.token_digits(6) verified ✓ SEC-06: OTP enumeration prevention: unknown phone → 200 not 404 ✓ SEC-07: OTP rate limit verification: automated test scripts ✓ SEC-08: Customer JWT isolation: separate signing keys verified ✓ SEC-09: PII encryption audit: AES-256-GCM key + IV + no plaintext in DB ✓ SEC-10 to SEC-16: PKCE, prompt injection, geofence fraud, QR entropy, Celery idempotency, WebSocket security ✓ SEC-17 to SEC-24: Full penetration test (auth bypass, OTP attacks, injection, OWASP ZAP, Burp Suite manual) ✓ SEC-25 to SEC-28: Remediation verification, SECURITY.md, RUNBOOK.md, 17-point pre-launch sign-off ✓ SEC-29 to SEC-30: Production security monitoring + incident response drills Collaborates with: All developers — every auth, OTP, encryption, or RLS PR requires Security Dev review and approval before merge. Key skills: Python, SQL, OWASP methodology, Burp Suite, OWASP ZAP, bandit, trivy, cryptography, JWT attack vectors, SQL injection testing, threat modeling

📋 Product Manager Owns: ✓ Sprint planning + ticket prioritisation ✓ Pilot restaurant onboarding ✓ UX review of all Stitch.ai-generated screens before API wiring ✓ Success metric tracking: OTP adoption rate, MRR, churn, NPS ✓ Stakeholder communication + v1.1 roadmap after launch Collaborates with: Security Dev for phase-gate sign-offs — Security Dev must sign off before each phase transition. Key skills: Jira/Linear, Figma (for UX review), analytics tools

→  3.2  Task Assignment Matrix (RACI)

R = Responsible  A = Accountable  C = Consulted  I = Informed

| Ticket / Task | Back 1 | Back 2 | Front | DevOps | QA | 🔐 Sec Dev |
| --- | --- | --- | --- | --- | --- | --- |
| INFRA-01 Project Skeleton | R | C | C | R | I | C |
| INFRA-02 PostgreSQL + PostGIS | C | R | I | C | I | C |
| INFRA-03 Redis + Celery | C | R | I | C | I | C |
| 🔐 SEC-01 Threat Model | C | C | I | I | I | R |
| 🔐 SEC-02 CI Security Toolchain | I | I | I | C | I | R |
| AUTH-01/02/03 Owner/Staff Auth | R | C | C | I | A | A |
| 🔐 SEC-03 Auth Security Audit | C | I | I | I | C | R |
| AUTH-04 RBAC Guards | R | C | I | I | A | A |
| 🔐 SEC-04 RLS Policy Audit | I | C | I | I | C | R |
| NEW-OTP-01/02 Customer OTP | R | C | C | I | A | A |
| 🔐 SEC-05 OTP Crypto Audit | C | I | I | I | C | R |
| 🔐 SEC-06 Enumeration Prevention | C | I | I | I | C | R |
| 🔐 SEC-07 Rate Limit Tests | C | I | I | I | C | R |
| 🔐 SEC-08 JWT Isolation | C | I | I | I | C | R |
| 🔐 SEC-09 PII Encryption Audit | C | C | I | I | C | R |
| 🔐 SEC-10 Stripe Webhook Sec | C | I | I | I | C | R |
| NEW-OTP-03 Registration | R | C | C | I | A | A |
| TENANT-01/02 Multi-Tenancy | C | R | I | C | A | C |
| SUB-01/02/03 Billing + Gating | R | C | C | I | A | C |
| REVIEW-01/02 Review Engine | R | C | I | I | A | I |
| REVIEW-03 GMB OAuth | R | C | I | I | A | A |
| 🔐 SEC-11 PKCE Audit | C | I | I | I | C | R |
| 🔐 SEC-12 Prompt Injection | C | I | I | I | C | R |
| LOYALTY-01/02 Branch + QR | C | R | C | I | A | C |
| LOYALTY-03 Geofence + Stamp | C | R | I | I | A | C |
| 🔐 SEC-13 Geofence Fraud | I | C | I | I | C | R |
| 🔐 SEC-14 QR Token Entropy | I | C | I | I | C | R |
| LOYALTY-04 Rewards | R | C | I | I | A | I |
| 🔐 SEC-15 Celery Idempotency | C | C | I | I | C | R |
| 🔐 SEC-16 WebSocket Security | C | C | I | I | C | R |
| DASH-01/02 Dashboard + Analytics | C | C | R | I | A | I |
| Stitch.ai All Screens | I | I | R | I | C | C |
| ADMIN-01 Super Admin Panel | R | C | C | I | A | A |
| Docker + CI/CD Pipeline | C | C | I | R | C | C |
| Load Testing (Locust) | I | C | I | R | R | I |
| 🔐 SEC-17 to 24 Full Pen Test | C | C | I | C | C | R |
| 🔐 SEC-25 Remediation Verify | C | C | I | I | C | R |
| 🔐 SEC-28 Pre-Launch Sign-Off | A | A | A | A | A | R |
| 🔐 SEC-29/30 Security Monitor | I | I | I | C | I | R |
| Pre-launch Functional QA | A | A | A | A | R | A |

→  3.3  Collaboration Rules  (Updated for 7-Person Team)

| Rule | How It Works |
| --- | --- |
| Daily standup (15 min) | All 7 team members. Cover: what I built, what I'm building today, blockers. |
| API Contract First | Backend Dev defines Pydantic schemas before writing code. Frontend Dev reviews. No guessing. |
| Stitch.ai Review Gate | Every screen reviewed by PM before wiring to API. Security Dev checks for CSP-compatible HTML. |
| 🔐 Security PR Gate | EVERY PR modifying auth, OTP, encryption, or RLS code requires Security Dev approval before merge. No exceptions. CI runs bandit automatically. |
| PR required for main | No direct pushes to main. Every change requires PR with at least 1 reviewer. CI must pass (including bandit + trivy). |
| Ticket states | todo → in-progress → in-review → done. No ticket stays 'in-progress' > 3 days without standup flag. |
| Blocked = escalate immediately | Any blocker > 4 hours is escalated to PM. Sprint velocity is protected. |
| 🔐 Security findings = stop-work | If Security Dev raises Critical or High finding on an endpoint/feature, development on that area stops until remediation verified. No new features ship on top of known vulnerabilities. |
| Env variables | Never commit secrets. git-secrets hook on all commits. DevOps + Security Dev co-manage AWS Secrets Manager. |
| 🔐 Phase gate sign-off | Security Dev must sign off before each phase transition: Foundation → OTP, OTP → Core Features, Core → Pen Test, Pen Test → Staging, Staging → Production. PM cannot authorise production deploy without Security Dev sign-off. |